## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2 | note
1 | As an Investor I should receive activation mail when I try to sgin up | 8 | Monica | Malak | Fady Medhat
1.1 | As a User I should be able to receive mail to reset password when I forget it | 8 | Fady Medhat | Malak | Monica
1.2 | The system should be able to send emails to notify users. | 5 | Malak | Monica | Fady Medhat | write a function that takes email and message as parameters
1.3 | The system should notify external entities of new companies and send company documents | 5 | Monica | Malak | Fady Medhat | Attach documents
1.4 | The user should be able to view the website in English and in Arabic | 3 | Malak | Monica | Fady Medhat | Function that changes local variable from 0 to 1, ask more about this
1.5 | The Investor should receive an Invoice by mail upon paying fees | 5 | Fady Medhat | Malak | Monica | coordinate with Ramy
1.6 | The Investor should receive automated emails whenever the Case changes status | 5 | Malak | Monica | Fady Medhat
1.7 | As an Admin I should be able to change pricing strategy | 2 | Fady Medhat | Malak | Monica | global variables
1.7 | Generating Form UI and Schema from JSON | 12 | Ramy&Fady | Nadeen | Paul | Epic: Ask more about this
1.8 | As an Admin I should be able to delete an Investor | 3 | Fady Hemaya | Ramy | Nadeen | Delete all dependencies
1.9 | As an Admin I should be able to delete a Case or a published Company | 3 | Nadeen | Ramy | Fady Hemaya
2 | As an Admin I should be able to delete a question | 2 | Nadeen | Ramy | Fady Hemaya
2.1 | As an Admin I should be able to delete a Staff member | 5 | Ramy | Nadeen | Fady Hemaya | Reassign Staff to their corresponding cases
2.2 | As an Investor I should be able to rate employee performance for each case | 3 | Nadeen | Ramy | Fady Hemaya | can add multiple reviews for same employee but if different cases
2.3 | As an Admin I am able to view ratings of a given lawyer or reviewer | 3 | Nadeen | Ramy | Fady Hemaya
2.4 | As an Admin I am able to register a lawyer and reviewer | 3 | Fady Hemaya | Nadeen | Ramy
2.5 | As an Admin I should be able to edit Company details | 2 | Ramy | Nadeen | Fady Hemaya
2.6 | The system should be able to generate a PDF format contract and store it | 8 | Paul | Sara | Daniel | function that generates a contract in PDF format from Case
2.7 | The system should be able to generate a PDF format Decision and store it | 3 | Paul | Sara | Daniel | Ask more about this
2.8 | As a User I should be able to upload and edit my profile picture | 8 | Daniel | Sara | Paul
2.9 | As an Investor I should be able to upload official documents to the system | 5 | Sara | Paul | Daniel
3 | As an Admin I should be able to see number of completed cases of a lawyer/reviewer | 2 | Sara | Paul | Daniel
3.1 | As an Admin I should be able to see avg number of completed cases per week of a lawyer/reviewer | 3 | Daniel | Sara | Paul
3.2 | As a staff member I should be able to view a leaderboard of who completed most cases | 3 | Sara | Sara | Paul