## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2 | notes
1 | As an Investor I should be able to pay fees | 12 | Ramy & Fady Hemaya | Nadeene | Monica
1.1 | As an Unregistered user I should be able to see the profile of different user | 2 | Nadeene | Ramy | Fady Hemaya
1.2 | As an Unregistered user I should be able to see list of different investors | 2 | Nadeene | Ramy | Fady Hemaya
1.3 | As an Unregistered user I should be able to see company info | 1 | Nadeene | Ramy | Fady Hemaya
1.4 | As an Unregistered user I should be able to ask a question | 1 | Nadeene | Ramy | Fady Hemaya
1.5 | As an Unregistered user I should be able to view questions and answers | 1 | Fady Hemaya | Ramy | Nadeene
1.6 | As an Unregistered user I should be able to view board of directors of certain company | 2 | Fady Hemaya | Ramy | Nadeene
1.7 | As an Unregistered user I should be able to view a list of different companies | 2 | Nadeene | Ramy | Fady Hemaya
1.8 | As an Unregistered user I should be able to sign up | 2 | Ramy | Nadeene | Fady Hemaya
1.9 | the system should compute avg time taken per case for staff member | 3 | Paul | Sara | Daniel
2 | As an Investor/Staff I should be able to change my password | 2 | Paul | Sara | Daniel
2.1 | As an Investor/Staff I should be able to view my notifications | 1 | Paul | Sara | Daniel
2.2 | As an Investor/Lawyer I should be able to fill a form | 3 | Sara | Paul | Daniel | only if the case is assigned to the lawyer
2.3 | As an Investor/Lawyer I should be able to update a form | 3 | Sara | Paul | Daniel | only if the case is assigned to the lawyer or my company
2.4 | As an Investor/Lawyer I should be able to view comments on a form | 2 | Sara | Paul | Daniel | only if the case is assigned to the lawyer or my company
2.5 | As an Investor/Staff I should be able to view my profile | 2 | Sara | Paul | Daniel
2.6 | As a Staff I should be able to view and comment on cases assigned to me | 2 | Daniel | Paul | Sara | coordinate with Monica (locking cases)
2.7 | As a Staff I should be able to approve and reject forms assigned to me | 2 | Daniel | Paul | Sara | coordinate with Monica (locking cases)
2.8 | As a staff I should be able view a list of my cases assigned to me | 2 | Daniel | Paul | Sara | coordinate with Monica (locking cases)
2.9 | As a staff I should be able view a list of unassigned cases | 2 | Paul | Sara | Daniel
3 | As a staff I should be able choose an unassigned case | 2 | Daniel | Paul | Sara
3.1 | As an Investor I Should be able to view a list of my companies | 1 | Paul | Sara | Daniel
3.2 | The system should validate the form according to the rules | 5 | Monica | Fady Medhat | Malak
3.3 | The system should calculate fees according to the form | 3 | Fady Medhat | Monica | Malak
3.4 | The system should keep track of time taken to complete a case | 2 | Malak | Monica | Fady Medhat
3.5 | As an Investor/Lawyer I should be able to view fees according to form | 2 | Malak | Monica | Fady Medhat | only if the case is assigned to the lawyer or my company
3.6 | The system should assign cases automatically and lock cases assigned | 3 | Fady Medhat | Monica | Malak | coordinate with monica and daniel
3.7 | As an Admin I should be able to assign cases to a lawyer and a reviewer | 2 | Monica | Fady Medhat | Malak | coordinate with malak and daniel
3.8 | The system should publish a Company and board of directors once the form is approved | 3 | Malak | Monica | Fady Medhat | coordinate with daniel (approving form)
3.9 | As an Investor I should be able to track case | 3 | Fady Medhat | Monica | Malak