## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | Create an Investor instance | 2 | Ramy | Investor
1.1 | Edit an Investor instance | 2 | Ramy | Investor
1.2 | Delete an Investor instance | 1 | Ramy | Investor
1.3 | Read all Investor instances | 1 | Ramy | Investor
1.4 | Read Investor Instance by ID | 1 | Ramy | Investor
1.5 | Create a Company instance | 2 | Paul | Company
1.6 | Edit a Company instance | 2 | Paul | Company
1.7 | Delete a Company instance | 1 | Paul | Company
1.8 | Read all Company instances | 1 | Paul | Company
1.9 | Read Company Instance by ID | 1 | Paul | Company
2 | Create Staff instance | 2 | Fady Hemaya | Staff
2.1 | Edit Staff instance | 2 | Fady Hemaya | Staff
2.2 | Delete Staff instance | 1 | Fady Hemaya | Staff
2.3 | Read all Staff instances | 1 | Fady Hemaya | Staff
2.4 | Read Staff Questions by ID | 1 | Fady Hemaya | Staff
2.5 | Create a Question instance | 2 | Monica | Question
2.6 | Edit a Question instance | 2 | Monica | Question
2.7 | Delete a Question instance | 1 | Monica | Question
2.8 | Read all Question instances | 1 | Monica | Question
2.9 | Read Question Instance by ID | 1 | Monica | Question
3 | Create a Form instance | 2 | Fady Medhat | Form
3.1 | Edit a Form instance | 2 | Fady Medhat | Form
3.2 | Delete a Form instance | 1 | Fady Medhat | Form
3.3 | Read all Forms instances | 1 | Fady Medhat | Form
3.4 | Read Form Instance by ID | 1 | Fady Medhat | Form
3.5 | Create a Case instance | 2 | Malak | Case
3.6 | Edit a Case instance | 2 | Malak | Case
3.7 | Delete a Case instance | 1 | Malak | Case
3.8 | Read all Case instances | 1 | Malak | Case
3.9 | Read Case Instance by ID | 1 | Malak | Case
4 | Create a Notification istance | 2 | Daniel | Notification
4.1 | Edit a Notification instance | 2 | Daniel | Notification
4.2 | Delete a Notification instance | 1 | Daniel | Notification
4.3 | Read all Notification instances | 1 | Daniel | Notification
4.4 | Read Notification Instance by ID | 1 | Daniel | Notification
4.5 | Create a Board of directors instance | 2 | Sara | Board of Directors
4.6 | Edit a Board of directors instance | 2 | Sara | Board of Directors
4.7 | Delete a Board of directors instance | 1 | Sara | Board of Directors
4.8 | Read all Board of directors instances | 1 | Sara | Board of Directors
4.9 | Read Board of directors Instance by ID | 1 | Sara | Board of Directors
5 | Create a Comment istance | 2 | Nadeene | Comment
5.1 | Edit a Comment instance | 2 | Nadeene | Comment
5.2 | Delete a Comment instance | 1 | Nadeene | Comment
5.3 | Read all Comments instances | 1 | Nadeene | Comment
5.4 | Read Comment Instance by ID | 1 | Nadeene | Comment